## Matrix
Req # | RFP ref | Requirement (verbatim or tight excerpt) | Type | Answer location (our §) | Owner | Status | Evidence / proof | Notes
R-001 | §3.1, p.7 | The Contractor must provide helpdesk coverage 24x7 with a one-hour response target for Priority 1 incidents. | Mandatory | §4 Service model | A. Rivera (Ops) | Final | SLA one-pager v3 + on-call roster | confirm wording matches the SLA document exactly
R-002 | §3.4, p.9 | Proposer will describe its approach to migrating 1,200 workstations from the legacy endpoint agent. | Mandatory | §5 Transition plan | J. Chen | Drafting | case study MIG-2025-02 | page budget shared with R-005; amendment 1 moved deadline
R-003 | §4.2, p.12 | Provide three references for contracts of similar size within the last five years. | Mandatory | §8 References | S. Patel | Assigned | library reference sheet; 2 client consents in hand | ask M. Ortiz for the third reference
R-004 | §5.1, p.15 | Proposer shall complete and return Form C-2 (Conflict of Interest Disclosure). | Form | Attachment C-2 | S. Patel | Final | signed PDF in deal folder | needs approver countersign — submission-day checklist item
R-005 | §3.9, p.10 | Describe the reporting dashboard and the monthly service review cadence offered. | Desirable | §6 Reporting | J. Chen | Drafting | report-pack screenshots + sample monthly report | reuse the municipal case-study chart
R-006 | §6.3, p.18 | Pricing must be submitted in the provided cost workbook, separate from the technical volume. | Mandatory | Cost workbook (separate file) | A. Rivera (Ops) | Assigned | pricing model tab drafted | no pricing language anywhere in the technical volume
R-007
R-008
R-009
R-010
R-011
R-012
R-013
R-014
R-015
R-016
R-017
R-018
R-019
R-020
R-021
R-022
R-023
R-024
R-025
R-026
R-027
R-028
R-029
R-030
R-031
R-032
R-033
R-034
R-035
R-036
R-037
R-038
R-039
R-040
R-041
R-042
R-043
R-044
R-045
R-046
R-047
R-048
R-049
R-050
R-051
R-052
R-053
R-054
R-055
R-056
R-057
R-058
R-059
One row per requirement (compound asks = several rows; forms and formatting rules get rows too). Verbatim text first — you re-read it at review time. Status: Shredded → Assigned → Drafting → Reviewed → Final; the pre-submit gate is 'sort by status, zero non-Final Mandatory rows'. Italic rows are examples from a fictional municipal IT-support RFP — overwrite them. SOP: shredding-sop.md

## Coverage
Coverage — counts update themselves from the Matrix sheet
By status
Status | Count
Shredded
Assigned
Drafting
Reviewed
Final
By type
Type | Count
Mandatory
Desirable
Form
Information
Mandatory compliance
Mandatory rows Final / total
All rows Final / total
The submission gate: every Mandatory row Final, and every Form row Final. Reviewers sign the matrix (red-team Round 1) — this sheet is the scoreboard they sign against.

## Amendments
Date | Type | What changed / what was answered | Matrix rows affected | Rows updated by | Done?
2026-09-18 | Amendment 1 | Deadline moved Oct 15 → Oct 22; §5.1 adds Form C-4 (insurance disclosure) — new Form row required | intake form + calendar + add row R-007 | S. Patel | Yes
2026-09-21 | Q&A #4 | Buyer confirms the legacy agent inventory list is available on request — reduces the migration unknown | R-002 (Notes) | J. Chen | Yes
Log every amendment and every material Q&A reply the day it arrives, name the matrix rows it touches, and mark Done only when those rows actually changed. An amendment you did not log is an evaluator instruction you did not follow. SOP: shredding-sop.md